## Sheet1
Activity | Engineering Time |  | Running Cost | Facility Use | Capital Cost | MMW |  | MMW | Total
[6 empty] | Labour |  | Material
| hr | R | R | R | R | hr | R | R | R
Literature Review | 15 | 6750 | 150 | [5 empty] | 6900
Component Review | 20 | 9000 | 150 | [5 empty] | 9150
Compile Design Requirements for Laparoscope | 20 | 9000 | 150 | [5 empty] | 9150
Generate Concept Design for Laparoscope | 35 | 15750 | 150 | [5 empty] | 15900
Finalise Detail Design for Laparoscope | 40 | 18000 | 150 | [5 empty] | 18150
Compile Design Requirements for Test Station | 20 | 9000 | 150 | [5 empty] | 9150
Generate Concept Design for Test Station | 30 | 13500 | 150 | [5 empty] | 13650
Finalise Detail Design for Test Station | 40 | 18000 | 150 | [5 empty] | 18150
Constuct and Implement Laparoscope | 95 | 42750 | 600 | 6000 | 4000 | 15 | 4500 | 500 | 58350
Construct Test Station | 20 | 9000 | 600 | 2000 |  | 40 | 12000 | 300 | 23900
Perform Functionality Test | 40 | 18000 | 600 | 2000 |  |  |  |  | 20600
Evaluate Laparoscope | 25 | 11250 | 150 | [5 empty] | 11400
Documentation | 120 | 54000 | 150 | [5 empty] | 54150
Total | 520 | 234000 | 3300 | 10000 | 4000 | 55 | 16500 | 800 | 268600